## ZK_Bug_Report
Field | Value
Defect ID | BUG_F10_1-5
Date Reported | 2023-12-01
Module/Component | Home Page
Severity | High
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section links functionality
Description | "Navigation" section links doesn't open and doesn’t redirect user to the correct pages
Steps to Reproduce | 1.Enter the "Home" page "navigation" section. 2. Expand "hamburger" 3. Click on each link.
Expected Behavior | Then user clicking on each link, they should open and redirect user to the correct pages.
Actual Behavior | All three links doesn't open and doesn’t redirect user to the correct pages
Attachments | Video BUG_F10_1-5.mp4
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-02
Comments/Notes | This Bug common to mobile, tablet and mobile screens
Field | Value
Defect ID | BUG_F10_1-6
Date Reported | 2023-12-01
Module/Component | Home Page
Severity | High
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section logo functionality
Description | "Navigation" section logo doesn't redirect user to the home page
Steps to Reproduce | 1.Enter the "Home" page "navigation" section. 2. Click on the "payapi"logo.
Expected Behavior | Then user clicking on the logo, located at the top left side of the webpage, it should be clickable and should redirect user to the home page.
Actual Behavior | The logo doesn't redirect user to the home page
Attachments | Video BUG_F10_1-6.mp4
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-02
Comments/Notes | This Bug common to mobile, tablet and mobile screens
Field | Value
Defect ID | BUG_F10_1-7
Date Reported | 2023-12-01
Module/Component | Home Page
Severity | High
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section button functionality
Description | A button doesn’t navigate user to the email schedule form.
Steps to Reproduce | 1.Enter the "Home" page "navigation" section. 2. Expand the "hamburger" 3. Click on the "Shedule a Demo" button.
Expected Behavior | Then user clicking on a button with the text "Schedule a Demo", it should be clickable and navigate users to the email schedule form.
Actual Behavior | A button doesn’t navigate user to the email schedule form.
Attachments | Video BUG_F10_1-7.mp4
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-03
Comments/Notes | This Bug common to mobile, tablet and mobile screens
Field | Value
Defect ID | BUG_F10_1-8
Date Reported | 2023-12-01
Module/Component | Home Page
Severity | Low
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section design circle element fail
Description | Designed background half-circle element is too small
Steps to Reproduce | Enter the "Home" page and check "navigation" section design circle element.
Expected Behavior | Users should see a designed background half-circle element which meet design specification
Actual Behavior | Designed background half-circle element is too small - need to meet design specification
Attachments | BUG_F10_1-8.pnj
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-03
Comments/Notes
Field | Value
Defect ID | BUG_F10_1-9
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | Low
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section design pixel perfection acceptance fail.
Description | All "navigation" section elements should meet design pixel perfection.
Steps to Reproduce | 1.Enter the "Home" page "navigation" section. 2. Expand the "hamburger" 3. Check design requirements "navigation" section design pixel perfection.
Expected Behavior | All "navigation" section elements should meet design pixel perfection. The acceptable design deviation can be up to 5px.
Actual Behavior | Line element doesn’t meet pixel perfection acceptance.
Attachments | BUG_F10_1-9.png
Environment | Windows 11, Edge Version 119.0.2151.72 (Official build) (64-bit)
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes
Field | Value
Defect ID | BUG_F10_1-13
Date Reported | 2023-12-04
Module/Component | Home Page
Severity | Medium
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section design requirements fail
Description | "Navigation" section design has text from other section design
Steps to Reproduce | 1.Enter the "Home" page "navigation" section. 2. Expand the "hamburger" 3. Check design requirements.
Expected Behavior | Design should meet the requirements listed in Figma “Design System” part.
Actual Behavior | Epanded section has text from "Home" page "api" section design
Attachments | BUG_F10_1-13.png
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes
Field | Value
Defect ID | BUG_F10_1-9
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | Low
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section design pixel perfection acceptance fail.
Description | All "navigation" section elements should meet design pixel perfection.
Steps to Reproduce | 1.Enter the "Home" page "navigation" section. 2. Expand the "hamburger" 3. Check design requirements "navigation" section design pixel perfection.
Expected Behavior | All "navigation" section elements should meet design pixel perfection. The acceptable design deviation can be up to 5px.
Actual Behavior | Line element doesn’t meet pixel perfection acceptance.
Attachments | BUG_F10_1-9.png
Environment | Windows 11, Edge Version 119.0.2151.72 (Official build) (64-bit)
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes
Field | Value
Defect ID | BUG_F10_1-13
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | Medium
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section design requirements fail
Description | "Navigation" section design has text from other section design
Steps to Reproduce | 1.Enter the "Home" page "navigation" section. 2. Expand the "hamburger" 3. Check design requirements.
Expected Behavior | Design should meet the requirements listed in Figma “Design System” part.
Actual Behavior | Epanded section has text from "Home" page "api" section design
Attachments | BUG_F10_1-13.png
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes
Field | Value
Defect ID | BUG_F10_2-8
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | Low
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section design circle element fail
Description | Designed background half-circle element is not by design specification
Steps to Reproduce | Enter the "Home" page and check "navigation" section design circle element.
Expected Behavior | Users should see a designed background half-circle element which meet design specification
Actual Behavior | Designed background half-circle element doesn’t meet design specification
Attachments | BUG_F10_2-8.png
Environment | Windows 11, Edge Version 119.0.2151.72 (Official build) (64-bit)
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes
Field | Value
Defect ID | BUG_F10_3-8
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | Low
Priority
Reported By | Julija Valaikiene
Summary | "Navigation" section design circle element fail
Description | Designed background half-circle element is not by design specification
Steps to Reproduce | Enter the "Home" page and check "navigation" section design circle element.
Expected Behavior | Users should see a designed background circle element which meet design specification
Actual Behavior | Designed background circle element doesn’t meet design specification
Attachments | BUG_F10_3-8.mp4
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes

## Bug Report TEMPLE
Field | Value
Defect ID | BUG-001
Date Reported
Module/Component | [Module or Component Affected]
Severity | [High, Medium, Low] (Bussines Analytisc. Don't writte)
Priority | [High, Medium, Low] (Bussines Analytisc. Don't writte)
Reported By | [Name of Tester]
Summary | [Brief Description of the Defect]
Description | [Detailed Description of the Defect] (Optional)
Steps to Reproduce | [List of Steps to Reproduce the Issue]
Expected Behavior | [What Was Expected]
Actual Behavior | [What Actually Happened]
Attachments | [Screenshots, Log Files]
Environment | [Testing Environment Details]
Status | [Open, In Progress, Closed, Reopened]
Date Fixed | [Date when Fixed, if applicable]
Comments/Notes | [Additional Information or Notes]