## ZK_Bug_Report
Field | Value
Defect ID | BUG_F13_1-5
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | Low
Priority
Reported By | Julija Valaikiene
Summary | “implement“ section elements design pixel perfection fail
Description | “implement“ section text box explanation text should meet design pixel perfection
Steps to Reproduce | 1.Enter the "Home" page. 2. Go to "implement" section 3. Check design requirements for pixel perfection.
Expected Behavior | All “implement“ section elements should meet design pixel perfection. The acceptable design deviation can be up to 5px
Actual Behavior | Text box explanation text doesn’t meet design perfection acceptance
Attachments | BUG_F13_1-5.png
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes
Field | Value
Defect ID | BUG_F13_2-6
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | Medium
Priority
Reported By | Julija Valaikiene
Summary | “implement“ section design colors fail
Description | “implement“ section text box explanation font color fail
Steps to Reproduce | Enter the "Home" page and check “implement“ section text box font colors.
Expected Behavior | The colors should meet the requirements listed in Figma “Design System” part.
Actual Behavior | Text box explanaition font color doesn’t meet the color requirements
Attachments | BUG_F13_2-6
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes
Field | Value
Defect ID | BUG_F13_3-5
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | High
Priority
Reported By | Julija Valaikiene
Summary | “implement“ section elements design pixel perfection fail
Description | “implement“ section elements should meet design pixel perfection
Steps to Reproduce | 1.Enter the "Home" page. 2. Go to "implement" section 3. Check design requirements for pixel perfection.
Expected Behavior | Then user clicking on a button with the text "Schedule a Demo", it should be clickable and navigate users to the email schedule form.
Actual Behavior | All “implement“ section elements doesn't meet design pixel perfection
Attachments | BUG_F13_3-5
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes
Field | Value
Defect ID | BUG_F13_3-6
Date Reported | 2023-12-03
Module/Component | Home Page
Severity | Medium
Priority
Reported By | Julija Valaikiene
Summary | “implement“ section text box font color design fail
Description | “implement“ section text box explanation text font doesn't meet font color design requirements
Steps to Reproduce | Enter the "Home" page and check “implement“ section text box font colors.
Expected Behavior | The colors should meet the requirements listed in Figma “Design System” part.
Actual Behavior | Text box explanaition font color doesn’t meet the color requirements
Attachments | BUG_F13_3-6
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | In Progress
Date Fixed | 2023-12-04
Comments/Notes

## Bug Report TEMPLE
Field | Value
Defect ID | BUG-001
Date Reported
Module/Component | [Module or Component Affected]
Severity | [High, Medium, Low] (Bussines Analytisc. Don't writte)
Priority | [High, Medium, Low] (Bussines Analytisc. Don't writte)
Reported By | [Name of Tester]
Summary | [Brief Description of the Defect]
Description | [Detailed Description of the Defect] (Optional)
Steps to Reproduce | [List of Steps to Reproduce the Issue]
Expected Behavior | [What Was Expected]
Actual Behavior | [What Actually Happened]
Attachments | [Screenshots, Log Files]
Environment | [Testing Environment Details]
Status | [Open, In Progress, Closed, Reopened]
Date Fixed | [Date when Fixed, if applicable]
Comments/Notes | [Additional Information or Notes]