## FR12_Bug_Report
Field | Value
Defect ID | BUG-FR12_1-8 (BUG-FR12_2-7, BUG-FR12_1-7)
Date Reported | 2023-12-03
Module/Component | Home Page, "companies" section
Severity
Priority
Reported By | Ingrida Zadorožnienė
Summary | Figma design mismatch
Description | Wrong logos/names positions
Steps to Reproduce | Checking figma requirements
Expected Behavior | Logos/names positions should match the figma design, section heigh is bad (BUG-FR12_1-8)
Actual Behavior | Logos/names positions do not match the figma design, section heigh should match (BUG-FR12_1-8)
Attachments
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | Fixed
Date Fixed | 2023-12-03
Comments/Notes | The problem is the same on mobile, tablet, desktop devices
Field | Value
Defect ID | BUG-FR12_1-6 (BUG-FR12_2-5, BUG-FR12-5)
Date Reported | 2023-12-03
Module/Component | Home Page, "companies" section
Severity
Priority
Reported By | Ingrida Zadorožnienė
Summary | The link/button is not working
Description | Button "About Us" is not linkable
Steps to Reproduce | 1. Go to "Home" page. 2. Go to "companies" section. 3. Click the "About Us" button.
Expected Behavior | Button "About Us" should open and redirect the user to the corresponding page
Actual Behavior | Button "About Us" does not open and redirect the user to the corresponding page
Attachments
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | Fixed
Date Fixed | 2023-12-03
Comments/Notes | The problem is the same on mobile, tablet, desktop devices
Field | Value
Defect ID | BUG-FR12_2-1,2,3
Date Reported | 2023-12-03
Module/Component | Home Page, "companies" section
Severity
Priority
Reported By | Ingrida Zadorožnienė
Summary | Bad alignment
Description | Left part of section is badly aligned
Steps to Reproduce | Checking AC requirements (figma design)
Expected Behavior | Left part of section should be feft aligned
Actual Behavior | Left part of section is aligned through the middle
Attachments
Environment | Windows 11, Chrome Version 119.0.6045.160
Status | Fixed
Date Fixed | 2023-12-03
Comments/Notes